## Quality Control Template
Quality Control
Issue | Description | Imperfections | Identified By | To Be Fixed By | Priority | Status | Date Opened | Date Closed | Notes
UI Bug/ Responsiveness | Buttons overlap on small screens | 9 | Nourhan | Shaden | High | Open | 2025-05-03
Database Error | Missing entries after form submission | 9 | Shaden | Noor | Medium | Closed | 2025-05-04 | 2025-05-10
Performance | Lag on homepage load | 5 | Noor | Alia | Medium | Open | 2025-05-05
Form Validation | Form accepts incomplete submissions | 6 | Shaden | Noor | Critical | Closed | 2025-05-06 | 2025-05-06
Navigation | Back button redirects to wrong page | 10 | Shaden | Noor | High | Closed | 2025-05-07 | 2025-05-07
Security | Password not encrypted in database | 8 | Nourhan | Alia | Critical | Open | 2025-05-08
API Error | Pet list API fails intermittently | 3 | Alia | Noor | Medium | Closed | 2025-05-09 | 2025-05-10
Data Sync | Adopted pets still visible as not adopted | 10 | Shaden | Noor | Critical | Closed | 2025-05-10 | 2025-05-11
Login Issue | Session expires too quickly | 5 | Noor | Nourhan | Medium | Closed | 2025-05-11 | 2025-05-12
Image Upload | Pet images not saving | 10 | Shaden | Alia | Critical | Closed | 2025-05-12 | 2025-05-13
Accessibility | Color contrast insufficient | 2 | Alia | Noor | Critical | Open | 2025-05-13
Search Function | Search gives unrelated results | 10 | Noor | Nourhan | Critical | Closed | 2025-05-14 | 2025-05-14 | Needs further testing
Filtering | Filter tags not working | 9 | Alia | Nourhan | High | Closed | 2025-05-15 | 2025-05-15 | Needs further testing
Page not loading | Next page shows same results | 10 | Noor | Shaden | Critical | Closed | 2025-05-16 | 2025-05-16
Notifications | Email confirmation not sent | 7 | Alia | Shaden | Critical | Open | 2025-05-17
Broken Link | Footer links redirect to 404 | 9 | Nourhan | Noor | High | Open | 2025-05-19
Crash | App crashes on submitting adoption | 10 | Alia | Noor | High | Open | 2025-05-20
Date Formatting | Adoption date in wrong format | 7 | Noor | Nourhan | Critical | Closed | 2025-05-21 | 2025-05-21