## Risk Tracking Template
Risk Register
Date of last review:
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
1 | Requirements are unclear or change frequently | Delay in delivery | Implement Agile, frequent meetings | High | Noor
2 | Insufficient knowledge of animal care regulations | Legal penalties, redesign of features | Consult experts early, compliance review | High | Hesham
3 | Poor integration with shelters' existing systems | Data loss, manual work increases | Early technical discovery, API planning | Medium | Development team | Prototype integrations early
4 | Security vulnerabilities | Data breaches | Regular security audits, secure coding | High | Dev Team / Security Officer | Implement encryption and authentication
5 | Rapid user adoption surpasses expectations | Faster growth and more donations | Ensure infrastructure can scale quickly | High | Shaden | Scalability, flexible architecture
6 | Limited budget for full functionality | Missing features at launch | Prioritize MVP features, phased releases | High | Sally | Manage stakeholder expectations
7 | Low adoption by shelters or users | Project failure | Early feedback loops, usability testing | High | Marketing Team
8 | System downtime during pet adoption events | Loss of revenue, bad reputation | Test under expected loads | Medium | Alia
9 | High user satisfaction leads to viral marketing | Increased adoption rates without extra marketing | Encourage and facilitate user reviews and sharing | High | Ahmed | Highlight happy adoption stories
10 | Negative publicity (adoption mistakes, mistreatment claims) | Brand damage | Clear T&C, prepare crisis communication plan | Medium | Mohamed
11 | Successful partnerships with large shelters | Access to more animals and users | Proactively seek and nurture partnerships | Medium | Sally
12 | Government grants for animal welfare tech | Additional funding to expand features | Monitor grant opportunities, apply early | Medium | Ahmed | Stay alert to new funding initiatives
13 | Shelter staff not trained to use the system | Errors, inefficiency | Training sessions, user manuals | Medium | Client Relations Manager | Provide onboarding material
14 | Animal profile inaccuracies (wrong data entered) | Legal and ethical issues | Validation processes, audits | Medium | Nourhan
15 | Media coverage boosts platform visibility | More trust and credibility | Engage with media | High | Sally | Be ready with positive impact stories
16 | Vendor delays (e.g., for hosting, APIs) | Project timeline shift | have backup vendors | Medium | Hesham
17 | Competition launches similar better platform | Loss of market share | Competitive analysis, feature innovation | High | Sally | Stay updated on industry
18 | Pet returns and complaints increase after adoption | Operational burden | Clear adoption agreements, post-adoption support | Medium | Mohamed